## Timeline Example
| NAME OF ORGANISATION: | ABC Company
| NAME OF PROJECT: | Upgrade Solar and Water Systems at XYZ School
| Project Start Date (dd/mmm/yyyy): | 15 Jan 2024
| Project End Date (dd/mmm/yyyy): | 30 Jun 2024
|  | 2023 |  |  | 2024 | [5 empty] | 2024
|  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1
Activity |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Cleaning the construction site | bar: Q3 Jan
Order and delivery of materials | bar: Q3 Jan
Installation of solar equipment | bar: Q4 Apr
Wiring of facility | bar: Q3 Feb to Q3 Mar
Installation of water pump | bar: Q4 Apr
Book keeper Training | bar: Q4 Jun
Print and installation of DAP Signage | bar: Q4 May to Q4 Jun
Opening ceremony | bar: Q4 Jun
Project Acquittal | bar: Q1 Jul
Please insert rows and columns as needed
Column1
2023
2024
2025
2026
2027
2028
2029
EXAMPLE

## Timeline template
NAME OF ORGANISATION:
NAME OF PROJECT:
Project Start Date (dd/mmm/yyyy):
Project End Date (dd/mmm/yyyy):
|  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1
Activity |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Please insert rows and columns as needed